## WBS — Full Breakdown
traindroid — Autonomous Android UI Testing Platform
Work Breakdown Structure & Prototype Estimate · May 2026
ID | Phase | Feature | Sub-Feature / Deliverable | Frontend (hrs) | Backend (hrs) | QA (hrs) | DevOps (hrs) | Database (hrs) | TOTAL (hrs)
Phase 0 — Project Setup
0.1 | Phase 0 — Project Setup | Repository & Monorepo Setup | Initialise Git repo, folder structure, README | 0 | 2 | 0 | 4 | 0 | 6
0.2 | Phase 0 — Project Setup | Docker Compose Skeleton | Node portal + Python test runner containers, networking | 0 | 2 | 1 | 6 | 0 | 9
0.3 | Phase 0 — Project Setup | Linting & Formatting Config | ESLint (JS), Black/Ruff (Python), pre-commit hooks | 1 | 2 | 0 | 1 | 0 | 4
0.4 | Phase 0 — Project Setup | Database Schema Design | ER diagram, table definitions (runs, steps, reports, users) | 0 | 2 | 0 | 0 | 6 | 8
0.5 | Phase 0 — Project Setup | Environment Config & Secrets | .env handling, secret management, config validation | 0 | 2 | 0 | 2 | 0 | 4
Phase 1 — APK Upload & Devices
1.1 | Phase 1 — APK Upload & Devices | APK Upload Endpoint | POST /upload — multipart form, file save, job queue entry | 0 | 4 | 2 | 0 | 0 | 6
1.2 | Phase 1 — APK Upload & Devices | APK Storage (Local Volume) | Disk path resolution, filename hashing, cleanup policy | 0 | 3 | 1 | 2 | 2 | 8
1.3 | Phase 1 — APK Upload & Devices | File Validation & Security Checks | MIME type check, file-size limit, APK header validation | 0 | 3 | 2 | 0 | 0 | 5
1.4 | Phase 1 — APK Upload & Devices | Android Emulator Docker Image | AVD creation, headless boot (-no-window), image optimisation | 0 | 0 | 2 | 12 | 0 | 14
1.5 | Phase 1 — APK Upload & Devices | ADB Connectivity Layer | adb connect, device list, install APK, launch app | 0 | 6 | 2 | 2 | 0 | 10
1.6 | Phase 1 — APK Upload & Devices | Emulator Health Checks & Pre-warm | Boot readiness polling, keep-alive between runs | 0 | 4 | 1 | 2 | 0 | 7
Phase 2 — AI Agent Engine
2.1 | Phase 2 — AI Agent Engine | Screenshot Capture | adb screencap → base64 encode → pass to LLM | 0 | 3 | 1 | 0 | 0 | 4
2.2 | Phase 2 — AI Agent Engine | UI Accessibility Tree Dump | uiautomator dump → parse XML → structured node list | 0 | 4 | 2 | 0 | 0 | 6
2.3 | Phase 2 — AI Agent Engine | LLM Integration — Tier 1 (text only) | Claude Haiku / GPT-4o-mini: text prompt, structured JSON response | 0 | 8 | 3 | 0 | 0 | 11
2.4 | Phase 2 — AI Agent Engine | LLM Integration — Tier 2 (vision) | Claude Sonnet / GPT-4o: image + tree, fallback trigger logic | 0 | 6 | 3 | 0 | 0 | 9
2.5 | Phase 2 — AI Agent Engine | Action Execution via ADB | tap, swipe, type, back — coordinate mapping from LLM response | 0 | 6 | 3 | 0 | 0 | 9
2.6 | Phase 2 — AI Agent Engine | Goal / Flow Parsing | Plain-English goal → structured sub-goals, success criteria | 0 | 6 | 2 | 0 | 0 | 8
2.7 | Phase 2 — AI Agent Engine | Agent Loop Orchestrator | Step driver: capture → reason → act → log → repeat | 0 | 10 | 4 | 0 | 0 | 14
2.8 | Phase 2 — AI Agent Engine | Stuck-Screen Detection | Compare consecutive screenshots; max-steps guard; abort logic | 0 | 4 | 2 | 0 | 0 | 6
2.9 | Phase 2 — AI Agent Engine | Confidence Threshold & Human Review Flag | Low-confidence trigger → pause run, flag for human review | 0 | 4 | 2 | 0 | 0 | 6
2.10 | Phase 2 — AI Agent Engine | Tiered Model Strategy Logic | Route decision: Tier 1 first, escalate to Tier 2 if needed | 0 | 4 | 2 | 0 | 0 | 6
Phase 3 — Screen Flow Testing
3.1 | Phase 3 — Screen Flow Testing | Flow Definition Format | JSON/YAML schema: steps, expected outcomes, success signals | 0 | 3 | 1 | 0 | 2 | 6
3.2 | Phase 3 — Screen Flow Testing | Flow Execution Engine | Step-by-step runner, pre/post conditions, branching | 0 | 8 | 3 | 0 | 0 | 11
3.3 | Phase 3 — Screen Flow Testing | Pass/Fail Detection Per Step | Expected element presence, text match, screen-hash compare | 0 | 4 | 3 | 0 | 0 | 7
3.4 | Phase 3 — Screen Flow Testing | Screenshot Capture on Failure | Auto-capture + annotate on any step failure | 0 | 2 | 1 | 0 | 0 | 3
Phase 4 — Functionality Testing
4.1 | Phase 4 — Functionality Testing | Input Simulation | Tap, swipe, long-press, type — coordinate + accessibility APIs | 0 | 4 | 2 | 0 | 0 | 6
4.2 | Phase 4 — Functionality Testing | Assertion Engine | Element presence, text value, enabled/disabled, visibility | 0 | 6 | 3 | 0 | 0 | 9
4.3 | Phase 4 — Functionality Testing | PyTest Integration & Test Runner | Fixture setup, parametrised test cases, CI-compatible output | 0 | 4 | 4 | 0 | 0 | 8
Phase 5 — Audit & Reporting
5.1 | Phase 5 — Audit & Reporting | Test Result Aggregation Service | Collect step results, compute run-level pass/fail, persist | 0 | 6 | 2 | 0 | 4 | 12
5.2 | Phase 5 — Audit & Reporting | Per-Step Audit Log | Timestamp, action, LLM reasoning, screenshot reference, status | 0 | 4 | 2 | 0 | 2 | 8
5.3 | Phase 5 — Audit & Reporting | HTML Report Generation | Jinja2 template: step table, embedded screenshots, summary | 2 | 4 | 2 | 0 | 0 | 8
5.4 | Phase 5 — Audit & Reporting | PDF Report Export | WeasyPrint / pdfkit render of HTML report | 1 | 3 | 1 | 0 | 0 | 5
5.5 | Phase 5 — Audit & Reporting | Report Storage & Retrieval API | Store report file, GET /report/:id endpoint, signed URL | 0 | 3 | 1 | 1 | 2 | 7
Phase 6 — Web Portal
6.1 | Phase 6 — Web Portal | App Shell, Routing & Auth Layout | React/Next.js scaffold, protected routes, nav sidebar | 8 | 2 | 2 | 0 | 0 | 12
6.2 | Phase 6 — Web Portal | APK Upload Screen | Drag-and-drop upload, progress bar, validation feedback | 8 | 2 | 2 | 0 | 0 | 12
6.3 | Phase 6 — Web Portal | Test Run Configuration Screen | Goal input, model tier selector, run name, submit | 6 | 2 | 2 | 0 | 0 | 10
6.4 | Phase 6 — Web Portal | Live Test Run Progress View | WebSocket feed, step timeline, live screenshot carousel | 10 | 4 | 3 | 0 | 0 | 17
6.5 | Phase 6 — Web Portal | Results / Audit Review Screen | Step-by-step audit table, screenshots, pass/fail badges | 8 | 2 | 3 | 0 | 0 | 13
6.6 | Phase 6 — Web Portal | Admin Approval Screen | Pending runs list, approve/reject buttons, sign-off timestamp | 6 | 2 | 2 | 0 | 0 | 10
Phase 7 — Admin Workflow
7.1 | Phase 7 — Admin Workflow | Super Admin User Model | User table, role enum, JWT auth for super-admin role | 1 | 3 | 1 | 0 | 3 | 8
7.2 | Phase 7 — Admin Workflow | Approve / Reject API Endpoint | PATCH /run/:id/approve¦reject, auth guard, state transition | 0 | 4 | 2 | 0 | 0 | 6
7.3 | Phase 7 — Admin Workflow | Final Report Release on Approval | Trigger report generation + storage only after approval | 0 | 3 | 1 | 0 | 0 | 4
7.4 | Phase 7 — Admin Workflow | Audit Sign-off Recording | Log who approved, when, any admin notes, immutable record | 0 | 2 | 1 | 0 | 2 | 5
Phase 8 — CI/CD Integration
8.1 | Phase 8 — CI/CD Integration | GitHub Actions Workflow | Trigger test run on push/PR, pass secrets, wait for result | 0 | 2 | 1 | 6 | 0 | 9
8.2 | Phase 8 — CI/CD Integration | Webhook / API Trigger | POST /trigger endpoint, HMAC signature validation, queue | 0 | 4 | 2 | 2 | 0 | 8
8.3 | Phase 8 — CI/CD Integration | Status Badge & Completion Callback | Badge SVG endpoint, POST callback URL on run completion | 0 | 3 | 1 | 2 | 0 | 6
8.4 | Phase 8 — CI/CD Integration | Docker Multi-Stage Build Optimisation | Slim production image, layer caching, build-arg injection | 0 | 0 | 1 | 6 | 0 | 7
Phase 9 — Platform QA
9.1 | Phase 9 — Platform QA | Unit Tests — Backend API | Jest/Pytest unit tests for all endpoints and helpers | 0 | 2 | 8 | 0 | 0 | 10
9.2 | Phase 9 — Platform QA | Integration Tests — Emulator Pipeline | Full pipeline test with a sample APK, assert audit output | 0 | 2 | 8 | 0 | 0 | 10
9.3 | Phase 9 — Platform QA | End-to-End Portal Tests | Playwright E2E: upload → run → review → approve flow | 2 | 0 | 10 | 0 | 0 | 12
9.4 | Phase 9 — Platform QA | Performance & Load Testing | Concurrent run stress test, emulator queue saturation | 0 | 0 | 6 | 2 | 0 | 8
9.5 | Phase 9 — Platform QA | Security Testing (OWASP Top 10) | File upload checks, auth bypass attempts, injection probes | 0 | 2 | 6 | 0 | 0 | 8
Subtotal — Phase 0 — Project Setup |  |  |  | 1 | 10 | 1 | 13 | 6 | 31
Subtotal — Phase 1 — APK Upload & Devices |  |  |  | 0 | 20 | 10 | 18 | 2 | 50
Subtotal — Phase 2 — AI Agent Engine |  |  |  | 0 | 55 | 24 | 0 | 0 | 79
Subtotal — Phase 3 — Screen Flow Testing |  |  |  | 0 | 17 | 8 | 0 | 2 | 27
Subtotal — Phase 4 — Functionality Testing |  |  |  | 0 | 14 | 9 | 0 | 0 | 23
Subtotal — Phase 5 — Audit & Reporting |  |  |  | 3 | 20 | 8 | 1 | 8 | 40
Subtotal — Phase 6 — Web Portal |  |  |  | 46 | 14 | 14 | 0 | 0 | 74
Subtotal — Phase 7 — Admin Workflow |  |  |  | 1 | 12 | 5 | 0 | 5 | 23
Subtotal — Phase 8 — CI/CD Integration |  |  |  | 0 | 9 | 5 | 16 | 0 | 30
Subtotal — Phase 9 — Platform QA |  |  |  | 2 | 6 | 38 | 2 | 0 | 48
GRAND TOTAL — PROTOTYPE BUILD |  |  |  | 53 | 177 | 122 | 50 | 23 | 425

## Summary Dashboard
traindroid — Prototype Effort Summary
Total estimated effort for a working prototype
| Discipline | Total Hours | % of Build | Equiv. Work Days (8h)
| Frontend | 53 | 12.47% | 6.625
| Backend | 177 | 41.65% | 22.125
| QA | 122 | 28.71% | 15.25
| DevOps | 50 | 11.76% | 6.25
| Database | 23 | 5.412% | 2.875
| TOTAL | 425 | 100% | 53.125
Hours by Phase
| Phase | FE | BE | QA | DevOps | DB | Total
| Phase 0 — Project Setup | 1 | 10 | 1 | 13 | 6 | 31
| Phase 1 — APK Upload & Devices | 0 | 20 | 10 | 18 | 2 | 50
| Phase 2 — AI Agent Engine | 0 | 55 | 24 | 0 | 0 | 79
| Phase 3 — Screen Flow Testing | 0 | 17 | 8 | 0 | 2 | 27
| Phase 4 — Functionality Testing | 0 | 14 | 9 | 0 | 0 | 23
| Phase 5 — Audit & Reporting | 3 | 20 | 8 | 1 | 8 | 40
| Phase 6 — Web Portal | 46 | 14 | 14 | 0 | 0 | 74
| Phase 7 — Admin Workflow | 1 | 12 | 5 | 0 | 5 | 23
| Phase 8 — CI/CD Integration | 0 | 9 | 5 | 16 | 0 | 30
| Phase 9 — Platform QA | 2 | 6 | 38 | 2 | 0 | 48
| TOTAL | 53 | 177 | 122 | 50 | 23 | 425
Estimation Assumptions
• Hours represent a single skilled developer per discipline (not parallelised headcount).
• 1 work day = 8 productive hours.
• Estimates assume Milestone 1 (MVP): local machine, headless AVD, Claude Haiku Tier 1 only.
• Phases 8–9 (CI/CD, platform QA) are post-MVP; include only if Milestone 2 is in scope.
• Database column covers schema design, migrations, and index tuning only — no DBA licence cost.
• AI API costs (per-run) are separate from build effort and are documented in PITCH.md.
• Contingency / integration buffer not included — recommend adding 20% to grand total.

## Milestone Plan
traindroid — Milestone-Scoped Effort Plan
Milestone 1 — MVP (Week 1)
Goal: Prove the core loop end-to-end: upload APK → AI tests → audit log → pass/fail
# | Deliverable | Description | FE | BE | QA | DevOps | DB | Total
1 |  | APK Upload Endpoint + local storage | 0 | 4 | 1 | 0 | 0 | 5
2 |  | Android Emulator Docker Image | 0 | 0 | 1 | 12 | 0 | 13
3 |  | ADB Connectivity Layer | 0 | 6 | 1 | 2 | 0 | 9
4 |  | LLM Integration — Tier 1 (Claude Haiku, text) | 0 | 8 | 2 | 0 | 0 | 10
5 |  | AI Agent Loop Orchestrator | 0 | 10 | 2 | 0 | 0 | 12
6 |  | Action Execution via ADB (tap/type/swipe) | 0 | 6 | 2 | 0 | 0 | 8
7 |  | Screenshot Capture + UI Tree Dump | 0 | 7 | 2 | 0 | 0 | 9
8 |  | Per-Step Audit Log | 0 | 4 | 1 | 0 | 2 | 7
9 |  | Basic HTML Pass/Fail Report | 2 | 4 | 1 | 0 | 0 | 7
10 |  | APK Upload Screen (portal) | 8 | 2 | 1 | 0 | 0 | 11
11 |  | Live Test Run Progress View (basic) | 6 | 2 | 2 | 0 | 0 | 10
12 |  | Results / Audit Review Screen (basic) | 4 | 2 | 1 | 0 | 0 | 7
13 |  | Docker Compose Skeleton | 0 | 2 | 1 | 6 | 0 | 9
14 |  | Database Schema (runs + steps) | 0 | 2 | 0 | 0 | 4 | 6
Milestone 1 — MVP (Week 1) Subtotal |  |  | 20 | 59 | 18 | 20 | 6 | 123
Milestone 2 — Hardening (Weeks 2–3)
Goal: Production-quality flow: vision fallback, admin approval, PDF export, Docker containerise
# | Deliverable | Description | FE | BE | QA | DevOps | DB | Total
1 |  | LLM Integration — Tier 2 (Sonnet, vision) | 0 | 6 | 2 | 0 | 0 | 8
2 |  | Tiered Model Strategy + Confidence Threshold | 0 | 8 | 2 | 0 | 0 | 10
3 |  | Stuck-Screen Detection & Max-Steps Guard | 0 | 4 | 2 | 0 | 0 | 6
4 |  | Multi-Flow / Configurable Goal Support | 0 | 6 | 2 | 0 | 0 | 8
5 |  | Flow Definition Format (JSON/YAML) | 0 | 3 | 1 | 0 | 2 | 6
6 |  | Pass/Fail Assertion Engine | 0 | 6 | 3 | 0 | 0 | 9
7 |  | PDF Report Export | 1 | 3 | 1 | 0 | 0 | 5
8 |  | Super Admin User Model + JWT Auth | 2 | 6 | 2 | 0 | 3 | 13
9 |  | Approve/Reject API + UI | 6 | 4 | 2 | 0 | 0 | 12
10 |  | Test Result Aggregation Service | 0 | 6 | 2 | 0 | 4 | 12
11 |  | Docker Multi-Stage Build Optimisation | 0 | 0 | 1 | 6 | 0 | 7
12 |  | Full Portal UI Polish (all screens) | 8 | 2 | 3 | 0 | 0 | 13
13 |  | Unit & Integration Tests | 0 | 4 | 10 | 0 | 0 | 14
Milestone 2 — Hardening (Weeks 2–3) Subtotal |  |  | 17 | 58 | 33 | 6 | 9 | 123
Milestone 3 — Scale (Month 2)
Goal: CI/CD integration, concurrent runs, RBAC, notifications, regression comparison
# | Deliverable | Description | FE | BE | QA | DevOps | DB | Total
1 |  | GitHub Actions Workflow | 0 | 2 | 1 | 6 | 0 | 9
2 |  | Webhook / API Trigger + HMAC | 0 | 4 | 2 | 2 | 0 | 8
3 |  | Status Badge & Completion Callback | 0 | 3 | 1 | 2 | 0 | 6
4 |  | Multiple Concurrent Test Runs | 0 | 8 | 3 | 2 | 0 | 13
5 |  | Regression Comparison (M1 vs current) | 0 | 8 | 4 | 0 | 2 | 14
6 |  | Role-Based Access (admin / tester) | 4 | 6 | 2 | 0 | 2 | 14
7 |  | Notification System (Slack / Email) | 0 | 6 | 2 | 0 | 0 | 8
8 |  | E2E Playwright Tests | 2 | 0 | 10 | 0 | 0 | 12
9 |  | Performance & Security Testing | 0 | 2 | 12 | 2 | 0 | 16
Milestone 3 — Scale (Month 2) Subtotal |  |  | 6 | 39 | 37 | 14 | 4 | 100
GRAND TOTAL (all milestones) |  |  | 43 | 156 | 88 | 40 | 19 | 346