## WBS — Full Breakdown
traindroid — Autonomous Android UI Testing Platform
Work Breakdown Structure & Prototype Estimate · v2.0 · May 2026
Tag legend: ★★★ Core Differentiator ¦ ★★ MVP Required ¦ ★ Milestone 2+ ¦ — Design / Discovery
ID | Phase | Feature | Sub-Feature / Deliverable | Priority / Tag | Frontend (hrs) | Backend (hrs) | QA (hrs) | DevOps (hrs) | Database (hrs) | TOTAL (hrs)
Phase D — UX & Product Design
D.1 | Phase D — UX & Product Design | User Research & Personas | Identify QA engineer, super-admin, and CI-trigger user journeys | — Design | 4 | 0 | 2 | 0 | 0 | 6
D.2 | Phase D — UX & Product Design | Information Architecture | Site map, screen inventory, navigation hierarchy | — Design | 4 | 0 | 0 | 0 | 0 | 4
D.3 | Phase D — UX & Product Design | Low-Fidelity Wireframes | All 6 portal screens: upload, config, progress, results, audit, admin | — Design | 8 | 0 | 2 | 0 | 0 | 10
D.4 | Phase D — UX & Product Design | High-Fidelity Mockups | Figma mockups with full colour, typography, spacing, component spec | — Design | 12 | 0 | 2 | 0 | 0 | 14
D.5 | Phase D — UX & Product Design | Design System / Component Library | Tokens: colour, type, spacing; Button, Card, Table, Badge components | — Design | 8 | 0 | 1 | 0 | 0 | 9
D.6 | Phase D — UX & Product Design | Interactive Prototype | Clickable Figma prototype for stakeholder sign-off walkthrough | — Design | 4 | 0 | 1 | 0 | 0 | 5
D.7 | Phase D — UX & Product Design | UX Review & Sign-Off | Stakeholder walkthrough, feedback incorporation, final approval | — Design | 2 | 0 | 1 | 0 | 0 | 3
D.8 | Phase D — UX & Product Design | Accessibility (a11y) Design Review | WCAG 2.1 AA check on mockups: contrast, focus order, ARIA labels | — Design | 2 | 0 | 2 | 0 | 0 | 4
Phase A — Architecture Design
A.1 | Phase A — Architecture Design | System Architecture Diagram | C4 context + container diagram: portal, runner, emulator, LLM, DB | — Design | 0 | 4 | 0 | 2 | 0 | 6
A.2 | Phase A — Architecture Design | API Contract Design (OpenAPI) | OpenAPI 3.1 spec for all endpoints; Swagger UI hosted on portal | — Design | 0 | 6 | 1 | 0 | 0 | 7
A.3 | Phase A — Architecture Design | Data Flow Diagrams | APK upload → queue → runner → LLM → audit → approval flow | — Design | 0 | 3 | 0 | 1 | 0 | 4
A.4 | Phase A — Architecture Design | Database ER Diagram | Tables: users, runs, steps, screenshots, reports, approvals | — Design | 0 | 2 | 0 | 0 | 4 | 6
A.5 | Phase A — Architecture Design | Architecture Decision Records (ADR) | ADR for: LLM provider, DB choice, queue strategy, Docker vs bare metal | — Design | 0 | 4 | 0 | 1 | 0 | 5
A.6 | Phase A — Architecture Design | Technology Spike — Emulator in Docker | PoC: headless AVD boots inside Docker on local machine (ARM + x86) | — Design | 0 | 0 | 2 | 12 | 0 | 14
A.7 | Phase A — Architecture Design | Technology Spike — LLM Action Schema | PoC: structured JSON action output from Claude Haiku via prompt eng. | — Design | 0 | 6 | 2 | 0 | 0 | 8
A.8 | Phase A — Architecture Design | Security Threat Model | STRIDE model for file upload, admin auth, and AI output trust boundary | — Design | 0 | 3 | 2 | 0 | 0 | 5
Phase 0 — Project Setup
0.1 | Phase 0 — Project Setup | Repository & Monorepo Setup | Git repo, folder structure, .gitignore, branch strategy, README | ★★ MVP | 0 | 2 | 0 | 4 | 0 | 6
0.2 | Phase 0 — Project Setup | Docker Compose Skeleton | Node portal + Python test runner containers, networks, volumes | ★★ MVP | 0 | 2 | 1 | 6 | 0 | 9
0.3 | Phase 0 — Project Setup | Linting & Formatting Config | ESLint (JS), Black/Ruff (Python), pre-commit hooks | ★★ MVP | 1 | 2 | 0 | 1 | 0 | 4
0.4 | Phase 0 — Project Setup | Environment Config & Secrets | .env handling, dotenv validation, secret rotation strategy | ★★ MVP | 0 | 2 | 0 | 2 | 0 | 4
0.5 | Phase 0 — Project Setup | Developer Environment Setup Guide | Step-by-step local dev setup; verify with fresh-clone checklist | ★★ MVP | 0 | 2 | 0 | 1 | 0 | 3
0.6 | Phase 0 — Project Setup | Database Schema & Migrations | Initial schema SQL, migration tool (Flyway / Alembic), seed data | ★★ MVP | 0 | 2 | 0 | 0 | 6 | 8
0.7 | Phase 0 — Project Setup | Job Queue Setup | Bull/BullMQ or Python RQ for async test run jobs | ★★ MVP | 0 | 4 | 1 | 2 | 0 | 7
Phase 1 — APK Upload & Self-Hosted
1.1 | Phase 1 — APK Upload & Self-Hosted | APK Upload Endpoint | POST /upload — multipart form, file save, job enqueue | ★★★ Core Diff | 0 | 4 | 2 | 0 | 0 | 6
1.2 | Phase 1 — APK Upload & Self-Hosted | Self-Hosted Local Volume Storage | Disk path resolver, SHA-256 filename hash, directory isolation | ★★★ Core Diff | 0 | 3 | 1 | 2 | 2 | 8
1.3 | Phase 1 — APK Upload & Self-Hosted | File Validation & Security Checks | MIME type, magic bytes, size cap, APK ZIP header check | ★★★ Core Diff | 0 | 3 | 2 | 0 | 0 | 5
1.4 | Phase 1 — APK Upload & Self-Hosted | APK Retention & Cleanup Policy | TTL-based deletion, manual purge endpoint, disk-space guard | ★★ MVP | 0 | 2 | 1 | 0 | 2 | 5
1.5 | Phase 1 — APK Upload & Self-Hosted | Android Emulator Docker Image | AVD creation, headless boot (-no-window), KVM/x86 emulation | ★★★ Core Diff | 0 | 0 | 2 | 12 | 0 | 14
1.6 | Phase 1 — APK Upload & Self-Hosted | ADB Connectivity Layer | adb connect, device ready poll, install APK, launch app, teardown | ★★★ Core Diff | 0 | 6 | 2 | 2 | 0 | 10
1.7 | Phase 1 — APK Upload & Self-Hosted | Emulator Health Check & Pre-warm | Boot readiness polling, keep-alive between runs, restart on crash | ★★ MVP | 0 | 4 | 1 | 2 | 0 | 7
1.8 | Phase 1 — APK Upload & Self-Hosted | Emulator Pool Manager | Queue-based slot allocation, single emulator for MVP, extendable | ★ M2+ | 0 | 6 | 2 | 2 | 0 | 10
Phase 2 — AI Agent Engine
2.1 | Phase 2 — AI Agent Engine | Screenshot Capture | adb screencap → PNG → base64 encode → attach to LLM payload | ★★★ Core Diff | 0 | 3 | 1 | 0 | 0 | 4
2.2 | Phase 2 — AI Agent Engine | UI Accessibility Tree Dump | uiautomator dump → XML parse → structured node dict | ★★★ Core Diff | 0 | 4 | 2 | 0 | 0 | 6
2.3 | Phase 2 — AI Agent Engine | LLM Prompt Engineering & Iteration | System prompt design, few-shot examples, JSON schema enforcement | ★★★ Core Diff | 0 | 8 | 2 | 0 | 0 | 10
2.4 | Phase 2 — AI Agent Engine | LLM Integration — Tier 1 (text) | Claude Haiku / GPT-4o-mini: accessibility tree → action JSON | ★★★ Core Diff | 0 | 6 | 3 | 0 | 0 | 9
2.5 | Phase 2 — AI Agent Engine | LLM Integration — Tier 2 (vision) | Claude Sonnet / GPT-4o: screenshot + tree → action JSON | ★★★ Core Diff | 0 | 6 | 3 | 0 | 0 | 9
2.6 | Phase 2 — AI Agent Engine | Action Response Schema Design | Pydantic/Zod schema: action_type, target, value, confidence, reason | ★★★ Core Diff | 0 | 4 | 2 | 0 | 0 | 6
2.7 | Phase 2 — AI Agent Engine | Action Execution via ADB | tap, swipe, long_press, type, back, scroll — ADB command mapper | ★★★ Core Diff | 0 | 6 | 3 | 0 | 0 | 9
2.8 | Phase 2 — AI Agent Engine | Goal / Flow Parsing | Plain-English goal → sub-goals + success criteria via LLM | ★★★ Core Diff | 0 | 6 | 2 | 0 | 0 | 8
2.9 | Phase 2 — AI Agent Engine | Agent Loop Orchestrator | Step driver: capture → reason → act → log → next step | ★★★ Core Diff | 0 | 10 | 4 | 0 | 0 | 14
2.10 | Phase 2 — AI Agent Engine | Tiered Model Routing Logic | Tier 1 first; escalate to Tier 2 on low-confidence flag | ★★★ Core Diff | 0 | 4 | 2 | 0 | 0 | 6
2.11 | Phase 2 — AI Agent Engine | Confidence Threshold & Review Flag | Score threshold → pause run → flag step for human review | ★★★ Core Diff | 0 | 4 | 2 | 0 | 0 | 6
2.12 | Phase 2 — AI Agent Engine | Stuck-Screen Detection | Pixel-hash comparison; max-steps guard; graceful abort + report | ★★ MVP | 0 | 4 | 2 | 0 | 0 | 6
2.13 | Phase 2 — AI Agent Engine | AI Cost Tracking per Run | Token counter middleware; log Tier 1 vs Tier 2 usage per run | ★ M2+ | 0 | 3 | 1 | 0 | 2 | 6
Phase 3 — Screen Flow Testing
3.1 | Phase 3 — Screen Flow Testing | Flow Definition Format (JSON/YAML) | Schema: steps, expected outcomes, branch conditions, success signal | ★★ MVP | 0 | 3 | 1 | 0 | 2 | 6
3.2 | Phase 3 — Screen Flow Testing | Flow Execution Engine | Step-by-step runner, pre/post conditions, conditional branching | ★★ MVP | 0 | 8 | 3 | 0 | 0 | 11
3.3 | Phase 3 — Screen Flow Testing | Pass/Fail Detection Per Step | Element presence, text match, screen-hash compare, timeout guard | ★★ MVP | 0 | 4 | 3 | 0 | 0 | 7
3.4 | Phase 3 — Screen Flow Testing | Screenshot Capture on Failure | Auto-capture + annotate (timestamp overlay) on any step failure | ★★ MVP | 0 | 2 | 1 | 0 | 0 | 3
3.5 | Phase 3 — Screen Flow Testing | Signup + Login Flow (Reference Flow) | Built-in flow: detect create-account, fill dummy creds, verify login | ★★ MVP | 0 | 4 | 2 | 0 | 0 | 6
Phase 4 — Functionality Testing
4.1 | Phase 4 — Functionality Testing | Input Simulation | Tap, swipe, long-press, type — coordinate + accessibility target | ★★ MVP | 0 | 4 | 2 | 0 | 0 | 6
4.2 | Phase 4 — Functionality Testing | Assertion Engine | Element presence, text value, enabled/disabled, visible/hidden | ★★ MVP | 0 | 6 | 3 | 0 | 0 | 9
4.3 | Phase 4 — Functionality Testing | PyTest Integration & Test Runner | Fixture setup, parametrised cases, JUnit XML output for CI | ★★ MVP | 0 | 4 | 4 | 0 | 0 | 8
Phase 5 — Audit & LLM Reasoning
5.1 | Phase 5 — Audit & LLM Reasoning | Per-Step Audit Log Model | Schema: timestamp, action, screenshot_id, status, llm_reasoning | ★★★ Core Diff | 0 | 4 | 2 | 0 | 2 | 8
5.2 | Phase 5 — Audit & LLM Reasoning | LLM Reasoning Narrative Formatter | Convert raw LLM JSON → human-readable prose per step (e.g. 'Detected signup screen…') | ★★★ Core Diff | 0 | 6 | 2 | 0 | 0 | 8
5.3 | Phase 5 — Audit & LLM Reasoning | Screenshot Storage & Retrieval | Save screenshots to volume, index by run+step, serve via API | ★★★ Core Diff | 0 | 3 | 1 | 1 | 2 | 7
5.4 | Phase 5 — Audit & LLM Reasoning | Test Result Aggregation Service | Roll up step results → run-level pass/fail + failure summary | ★★★ Core Diff | 0 | 6 | 2 | 0 | 2 | 10
5.5 | Phase 5 — Audit & LLM Reasoning | Audit Trail Immutability | Append-only log writes; no update/delete on audit rows post-run | ★★★ Core Diff | 0 | 2 | 1 | 0 | 2 | 5
5.6 | Phase 5 — Audit & LLM Reasoning | HTML Report Generation | Jinja2 template: step table, embedded screenshots, reasoning prose | ★★ MVP | 2 | 4 | 2 | 0 | 0 | 8
5.7 | Phase 5 — Audit & LLM Reasoning | PDF Report Export | WeasyPrint render of HTML report; download via portal | ★★ MVP | 1 | 3 | 1 | 0 | 0 | 5
5.8 | Phase 5 — Audit & LLM Reasoning | Report Storage & Retrieval API | Persist report file, GET /report/:id, serve on approval | ★★ MVP | 0 | 3 | 1 | 1 | 0 | 5
Phase 6 — Web Portal
6.1 | Phase 6 — Web Portal | App Shell, Routing & Auth Layout | React/Next.js scaffold, protected routes, responsive nav sidebar | ★★ MVP | 8 | 2 | 2 | 0 | 0 | 12
6.2 | Phase 6 — Web Portal | Design System Implementation | Translate Figma tokens → Tailwind/CSS vars; shared component lib | ★★ MVP | 8 | 0 | 2 | 0 | 0 | 10
6.3 | Phase 6 — Web Portal | APK Upload Screen | Drag-and-drop zone, progress bar, file info, validation feedback | ★★★ Core Diff | 8 | 2 | 2 | 0 | 0 | 12
6.4 | Phase 6 — Web Portal | Test Run Configuration Screen | Goal textarea, model tier selector, run name/tag, submit CTA | ★★ MVP | 6 | 2 | 2 | 0 | 0 | 10
6.5 | Phase 6 — Web Portal | Live Test Run Progress View | WebSocket feed, step timeline, live screenshot carousel, spinner | ★★ MVP | 10 | 4 | 3 | 0 | 0 | 17
6.6 | Phase 6 — Web Portal | Results / Audit Review Screen | Step-by-step audit table, LLM reasoning prose, pass/fail badges | ★★★ Core Diff | 8 | 2 | 3 | 0 | 0 | 13
6.7 | Phase 6 — Web Portal | Admin Approval Screen | Pending runs list, approve/reject, sign-off timestamp, notes input | ★★★ Core Diff | 6 | 2 | 2 | 0 | 0 | 10
6.8 | Phase 6 — Web Portal | Loading, Error & Empty States | Skeleton loaders, error banners, empty-state illustrations per screen | ★★ MVP | 4 | 0 | 2 | 0 | 0 | 6
6.9 | Phase 6 — Web Portal | Accessibility (a11y) Implementation | Keyboard navigation, ARIA labels, focus management, contrast audit | ★ M2+ | 4 | 0 | 3 | 0 | 0 | 7
Phase 7 — Admin Approval Workflow
7.1 | Phase 7 — Admin Approval Workflow | Super Admin User Model & Auth | User table, role enum, JWT login/refresh, bcrypt password hashing | ★★★ Core Diff | 1 | 4 | 2 | 0 | 3 | 10
7.2 | Phase 7 — Admin Approval Workflow | Approve / Reject API Endpoint | PATCH /run/:id/approve¦reject, auth guard, state machine transition | ★★★ Core Diff | 0 | 4 | 2 | 0 | 0 | 6
7.3 | Phase 7 — Admin Approval Workflow | Report Release Gating | Report file only served / generated after admin approval action | ★★★ Core Diff | 0 | 3 | 2 | 0 | 0 | 5
7.4 | Phase 7 — Admin Approval Workflow | Audit Sign-off Recording | Immutable record: approver, timestamp, admin notes, run_id FK | ★★★ Core Diff | 0 | 2 | 1 | 0 | 2 | 5
7.5 | Phase 7 — Admin Approval Workflow | Admin Notification (Email) | Send email on new run awaiting approval; configurable SMTP | ★ M2+ | 0 | 3 | 1 | 0 | 0 | 4
Phase 8 — CI/CD Integration
8.1 | Phase 8 — CI/CD Integration | GitHub Actions Workflow | Trigger test run on push/PR; poll for result; fail CI on test fail | ★ M2+ | 0 | 2 | 1 | 6 | 0 | 9
8.2 | Phase 8 — CI/CD Integration | Webhook / API Trigger Endpoint | POST /trigger; HMAC-SHA256 signature validation; job enqueue | ★ M2+ | 0 | 4 | 2 | 2 | 0 | 8
8.3 | Phase 8 — CI/CD Integration | Status Badge & Completion Callback | Badge SVG endpoint; POST callback URL on run completion | ★ M2+ | 0 | 3 | 1 | 2 | 0 | 6
8.4 | Phase 8 — CI/CD Integration | Docker Multi-Stage Build | Slim production image, layer caching, build-arg injection | ★ M2+ | 0 | 0 | 1 | 6 | 0 | 7
Phase 9 — Observability
9.1 | Phase 9 — Observability | Structured Logging (Winston/Pino) | JSON logs with run_id, step_id, level, duration on every service | ★★ MVP | 0 | 4 | 1 | 0 | 0 | 5
9.2 | Phase 9 — Observability | Error Tracking (Sentry) | Sentry SDK in Node + Python; alert on unhandled exceptions | ★★ MVP | 0 | 2 | 1 | 2 | 0 | 5
9.3 | Phase 9 — Observability | Health Check Endpoints | GET /health on portal + runner; Docker HEALTHCHECK integration | ★★ MVP | 0 | 2 | 1 | 1 | 0 | 4
9.4 | Phase 9 — Observability | Run Failure Alerting | Slack/email alert when a test run fails or gets stuck | ★ M2+ | 0 | 3 | 1 | 0 | 0 | 4
9.5 | Phase 9 — Observability | Basic Metrics Dashboard | Grafana + Prometheus: run count, success rate, avg duration | ★ M2+ | 0 | 0 | 1 | 6 | 0 | 7
9.6 | Phase 9 — Observability | LLM API Cost Monitoring | Per-run token usage logged; daily cost summary report | ★ M2+ | 0 | 2 | 1 | 0 | 2 | 5
Phase 10 — Documentation
10.1 | Phase 10 — Documentation | Developer Setup Guide | Clone → configure → run locally in < 15 min; tested on clean machine | ★★ MVP | 0 | 3 | 1 | 1 | 0 | 5
10.2 | Phase 10 — Documentation | API Reference (Swagger UI) | Auto-generated from OpenAPI spec; hosted at /api/docs | ★★ MVP | 0 | 2 | 1 | 0 | 0 | 3
10.3 | Phase 10 — Documentation | User Portal Guide | How to upload APK, configure a run, read audit report, approve | ★★ MVP | 2 | 0 | 1 | 0 | 0 | 3
10.4 | Phase 10 — Documentation | Deployment Guide (Self-Hosted) | Docker Compose prod setup, env vars, volume mounts, KVM prereqs | ★★ MVP | 0 | 3 | 0 | 2 | 0 | 5
10.5 | Phase 10 — Documentation | CONTRIBUTING.md & Coding Standards | PR process, branch naming, commit conventions, review checklist | ★ M2+ | 0 | 2 | 0 | 0 | 0 | 2
10.6 | Phase 10 — Documentation | Architecture Overview Document | Written summary of C4 diagrams, data flow, design decisions | ★ M2+ | 0 | 3 | 0 | 1 | 0 | 4
Phase 11 — Platform QA
11.1 | Phase 11 — Platform QA | Unit Tests — Backend API | Jest/Pytest unit tests for all endpoints, helpers, schemas | ★★ MVP | 0 | 2 | 8 | 0 | 0 | 10
11.2 | Phase 11 — Platform QA | Integration Tests — Emulator Pipeline | Full pipeline test with a sample APK; assert audit log output | ★★ MVP | 0 | 2 | 8 | 0 | 0 | 10
11.3 | Phase 11 — Platform QA | End-to-End Portal Tests (Playwright) | E2E: upload APK → run → live view → results → approve flow | ★ M2+ | 2 | 0 | 10 | 0 | 0 | 12
11.4 | Phase 11 — Platform QA | Performance & Load Testing | Concurrent run stress test, emulator queue saturation | ★ M2+ | 0 | 0 | 6 | 2 | 0 | 8
11.5 | Phase 11 — Platform QA | Security Testing (OWASP Top 10) | File upload checks, auth bypass, injection probes, JWT fuzz | ★★ MVP | 0 | 2 | 6 | 0 | 0 | 8
11.6 | Phase 11 — Platform QA | AI Output Validation Testing | Inject known screens; verify LLM action accuracy + reasoning prose | ★★ MVP | 0 | 2 | 6 | 0 | 0 | 8
Subtotal — Phase D — UX & Product Design |  |  |  |  | 44 | 0 | 11 | 0 | 0 | 55
Subtotal — Phase A — Architecture Design |  |  |  |  | 0 | 28 | 7 | 16 | 4 | 55
Subtotal — Phase 0 — Project Setup |  |  |  |  | 1 | 16 | 2 | 16 | 6 | 41
Subtotal — Phase 1 — APK Upload & Self-Hosted |  |  |  |  | 0 | 28 | 13 | 20 | 4 | 65
Subtotal — Phase 2 — AI Agent Engine |  |  |  |  | 0 | 68 | 29 | 0 | 2 | 99
Subtotal — Phase 3 — Screen Flow Testing |  |  |  |  | 0 | 21 | 10 | 0 | 2 | 33
Subtotal — Phase 4 — Functionality Testing |  |  |  |  | 0 | 14 | 9 | 0 | 0 | 23
Subtotal — Phase 5 — Audit & LLM Reasoning |  |  |  |  | 3 | 31 | 12 | 2 | 8 | 56
Subtotal — Phase 6 — Web Portal |  |  |  |  | 62 | 14 | 21 | 0 | 0 | 97
Subtotal — Phase 7 — Admin Approval Workflow |  |  |  |  | 1 | 16 | 8 | 0 | 5 | 30
Subtotal — Phase 8 — CI/CD Integration |  |  |  |  | 0 | 9 | 5 | 16 | 0 | 30
Subtotal — Phase 9 — Observability |  |  |  |  | 0 | 13 | 6 | 9 | 2 | 30
Subtotal — Phase 10 — Documentation |  |  |  |  | 2 | 13 | 3 | 4 | 0 | 22
Subtotal — Phase 11 — Platform QA |  |  |  |  | 2 | 8 | 44 | 2 | 0 | 56
GRAND TOTAL — PROTOTYPE BUILD |  |  |  |  | 115 | 279 | 180 | 85 | 33 | 692
[5 empty] | 230 | 558 | 360 | 170 | 66 | 1384 | 1522.4

## Summary Dashboard
traindroid — Prototype Effort Summary
Total estimated effort for a working prototype · v2.0 May 2026
Core Platform Differentiators (★★★)
| #1 | APK Upload → Self-Hosted — Phase 1 — no cloud lock-in; local volume; Docker-first
| #2 | Zero-Script AI Agent — Phase 2 — LLM reads screen, reasons, acts; no test code needed
| #3 | LLM Reasoning Audit Trail — Phase 5 — per-step human-readable narrative from the AI
| #4 | Admin Approval Workflow — Phase 7 — report gated behind super-admin sign-off
Effort by Discipline
| Discipline | Total Hours | % of Build | Equiv. Work Days (8 h)
| Frontend | 115 | 16.62% | 14.375
| Backend | 279 | 40.32% | 34.875
| QA | 180 | 26.01% | 22.5
| DevOps | 85 | 12.28% | 10.625
| Database | 33 | 4.769% | 4.125
| TOTAL | 692 | 100% | 86.5
Hours by Phase
| Phase | FE | BE | QA | DevOps / DB | Total
| Phase D — UX & Product Design | 44 | 0 | 11 | 0 | 55
| Phase A — Architecture Design | 0 | 28 | 7 | 20 | 55
| Phase 0 — Project Setup | 1 | 16 | 2 | 22 | 41
| Phase 1 — APK Upload & Self-Hosted | 0 | 28 | 13 | 24 | 65
| Phase 2 — AI Agent Engine | 0 | 68 | 29 | 2 | 99
| Phase 3 — Screen Flow Testing | 0 | 21 | 10 | 2 | 33
| Phase 4 — Functionality Testing | 0 | 14 | 9 | 0 | 23
| Phase 5 — Audit & LLM Reasoning | 3 | 31 | 12 | 10 | 56
| Phase 6 — Web Portal | 62 | 14 | 21 | 0 | 97
| Phase 7 — Admin Approval Workflow | 1 | 16 | 8 | 5 | 30
| Phase 8 — CI/CD Integration | 0 | 9 | 5 | 16 | 30
| Phase 9 — Observability | 0 | 13 | 6 | 11 | 30
| Phase 10 — Documentation | 2 | 13 | 3 | 4 | 22
| Phase 11 — Platform QA | 2 | 8 | 44 | 2 | 56
| TOTAL | 115 | 279 | 180 | 118 | 692
Estimation Assumptions
• Hours = single skilled developer per discipline; not parallelised headcount.
• 1 work day = 8 productive hours. Recommend +20% contingency on grand total.
• Phase D + A (Design) hours are Front-End effort; UX designer time is included in FE column.
• ★★★ Core Diff rows are the 4 differentiators that set traindroid apart from all competitors.
• ★★ MVP rows are required for Milestone 1 working prototype (Week 1 target).
• ★ M2+ rows are Milestone 2 or later; exclude from Week-1 scope.
• Database column: schema design, migrations, index tuning only — no DBA licence cost.
• AI API costs (per-run) are runtime costs, not build effort — see PITCH.md for breakdown.
• Emulator Docker spike (Phase A.6, 12h DevOps) may reduce once AVD-in-Docker is proven.

## Milestone Plan
traindroid — Milestone-Scoped Effort Plan
Milestone 0 — Design Sprint (Days 1–3)
Goal: Wireframes, architecture diagram, API contracts, emulator Docker spike, LLM prompt PoC
# | Deliverable | FE | BE | QA | DevOps | DB | Total
1 | User Research & Personas | 4 | 0 | 1 | 0 | 0 | 5
2 | Wireframes — all 6 portal screens | 8 | 0 | 1 | 0 | 0 | 9
3 | Hi-Fi Mockups + Design System tokens | 12 | 0 | 1 | 0 | 0 | 13
4 | System Architecture Diagram (C4) | 0 | 4 | 0 | 2 | 0 | 6
5 | API Contract Design (OpenAPI spec) | 0 | 6 | 1 | 0 | 0 | 7
6 | Database ER Diagram | 0 | 2 | 0 | 0 | 4 | 6
7 | ADR: LLM provider, DB, queue, Docker | 0 | 4 | 0 | 0 | 0 | 4
8 | Tech Spike — Emulator in Docker (PoC) | 0 | 0 | 1 | 12 | 0 | 13
9 | Tech Spike — LLM Action Schema (PoC) | 0 | 6 | 1 | 0 | 0 | 7
10 | Security Threat Model | 0 | 3 | 2 | 0 | 0 | 5
Milestone 0 — Design Sprint (Days 1–3) Subtotal |  | 24 | 25 | 8 | 14 | 4 | 75
Milestone 1 — MVP (Week 1)
Goal: Core loop: APK upload → AI agent tests → LLM reasoning audit log → pass/fail report
# | Deliverable | FE | BE | QA | DevOps | DB | Total
1 | Repo, Docker Compose, .env, DB schema | 0 | 6 | 1 | 8 | 6 | 21
2 | APK upload endpoint + self-hosted volume [★★★] | 0 | 4 | 2 | 0 | 2 | 8
3 | File validation + security checks [★★★] | 0 | 3 | 2 | 0 | 0 | 5
4 | Android Emulator Docker Image + ADB layer [★★★] | 0 | 6 | 2 | 12 | 0 | 20
5 | Screenshot capture + UI tree dump [★★★] | 0 | 7 | 2 | 0 | 0 | 9
6 | LLM prompt engineering + Tier 1 integration [★★★] | 0 | 14 | 3 | 0 | 0 | 17
7 | Agent loop orchestrator [★★★] | 0 | 10 | 3 | 0 | 0 | 13
8 | Action execution via ADB [★★★] | 0 | 6 | 2 | 0 | 0 | 8
9 | Per-step audit log + LLM reasoning narrative [★★★] | 0 | 10 | 3 | 0 | 4 | 17
10 | Audit trail immutability [★★★] | 0 | 2 | 1 | 0 | 2 | 5
11 | HTML + PDF report generation | 3 | 7 | 2 | 0 | 0 | 12
12 | Portal: App shell, upload screen, config screen | 14 | 4 | 3 | 0 | 0 | 21
13 | Portal: Live progress + results/audit screen | 18 | 6 | 4 | 0 | 0 | 28
14 | Portal: Admin approval screen + API [★★★] | 7 | 6 | 3 | 0 | 2 | 18
15 | Stuck-screen detection + max-steps guard | 0 | 4 | 2 | 0 | 0 | 6
16 | Structured logging + error tracking | 0 | 4 | 1 | 2 | 0 | 7
17 | Unit + integration tests (backend) | 0 | 4 | 8 | 0 | 0 | 12
18 | Security test pass (OWASP upload / auth) | 0 | 2 | 6 | 0 | 0 | 8
19 | Developer setup guide + API docs | 2 | 5 | 1 | 1 | 0 | 9
Milestone 1 — MVP (Week 1) Subtotal |  | 44 | 110 | 51 | 23 | 16 | 244
Milestone 2 — Hardening (Weeks 2–3)
Goal: Vision fallback, configurable goals, notifications, load/perf testing, Docker production build
# | Deliverable | FE | BE | QA | DevOps | DB | Total
1 | Tier 2 vision model + tiered routing logic | 0 | 10 | 3 | 0 | 0 | 13
2 | Confidence threshold + human review flag | 0 | 4 | 2 | 0 | 0 | 6
3 | Multi-flow / configurable goal support | 0 | 6 | 2 | 0 | 0 | 8
4 | Signup + Login reference flow (built-in) | 0 | 4 | 2 | 0 | 0 | 6
5 | Emulator pool manager (slot allocation) | 0 | 6 | 2 | 2 | 0 | 10
6 | Admin email notification on pending runs | 0 | 3 | 1 | 0 | 0 | 4
7 | AI cost tracking per run | 0 | 3 | 1 | 0 | 2 | 6
8 | Design system implementation + UI polish | 8 | 0 | 2 | 0 | 0 | 10
9 | Loading, error & empty states | 4 | 0 | 2 | 0 | 0 | 6
10 | E2E Playwright tests | 2 | 0 | 10 | 0 | 0 | 12
11 | Performance + load testing | 0 | 0 | 6 | 2 | 0 | 8
12 | Docker multi-stage production build | 0 | 0 | 1 | 6 | 0 | 7
13 | Metrics dashboard (Grafana + Prometheus) | 0 | 0 | 1 | 6 | 2 | 9
14 | Architecture overview doc + CONTRIBUTING.md | 0 | 5 | 0 | 1 | 0 | 6
Milestone 2 — Hardening (Weeks 2–3) Subtotal |  | 14 | 41 | 35 | 17 | 4 | 111
Milestone 3 — Scale (Month 2)
Goal: CI/CD integration, concurrent runs, RBAC, regression comparison, Slack notifications
# | Deliverable | FE | BE | QA | DevOps | DB | Total
1 | GitHub Actions workflow + HMAC webhook trigger | 0 | 6 | 2 | 8 | 0 | 16
2 | Status badge + completion callback | 0 | 3 | 1 | 2 | 0 | 6
3 | Multiple concurrent test runs (queue) | 0 | 8 | 3 | 2 | 0 | 13
4 | Regression comparison (baseline vs current) | 0 | 8 | 4 | 0 | 2 | 14
5 | Role-based access control (admin / tester) | 4 | 6 | 2 | 0 | 2 | 14
6 | Slack / email notification system | 0 | 6 | 2 | 0 | 0 | 8
7 | Accessibility (a11y) implementation | 4 | 0 | 3 | 0 | 0 | 7
8 | LLM API cost monitoring dashboard | 0 | 2 | 1 | 0 | 2 | 5
9 | User portal guide + deployment guide | 2 | 3 | 1 | 2 | 0 | 8
Milestone 3 — Scale (Month 2) Subtotal |  | 10 | 42 | 19 | 14 | 6 | 91
GRAND TOTAL (all milestones) |  | 92 | 218 | 113 | 68 | 30 | 521